## Benchmark Analysis
ITEM | BUILDING COMPONENTS | Normal Lifespan Years | Installation year | Year of Inspection | Actual Age | Effective Age Years | Remaining Lifespan Years | Quantity | Unit | Rate | Current Replacement Cost | Future Replacement Cost
1 | Superstructure - painting to steel fire escape stairs - 2 stairs | 7 | 2011 | 2017 | 6 | 6 | 1 | 2 | item | 200 | 400 | 408
2A | Superstructure - knock and remove chimney stack to east side of building | 75 | 1941 | 2017 | 76 | 74 | 1 | 1 | item | 6037.5 | 6037.5 | 6158.25
2B | Superstructure - re-point chimney stack for main boiler room in middle of building | 75 | 1928 | 2017 | 89 | 74 | 1 | 1 | item | 10080 | 10080 | 10281.6
3A | Exterior walls (stucco) at back corner - replacement | 75 | 1941 | 2017 | 76 | 73 | 2 | 1000 | sf | 21 | 21000 | 21848.4
3B | Exterior walls (stucco and cedar siding) - replacement | 75 | 1941 | 2017 | 76 | 55 | 20 | 12400 | sf | 21 | 260400 | 386940.7019
3C | Exterior walls (stucco and cedar siding) - painting | 10 | 2014 | 2017 | 3 | 3 | 7 | 13400 | sf | 1.25 | 16750 | 19240.4849
4A | Wooden framed single glazed windows - hall, offices & daycare - 46 ea | 60 | 1941 | 2017 | 76 | 50 | 10 | 46 | ea | 3000 | 138000 | 168221.23
4B | Wooden framed single glazed stained windows - church - 9 large windows | 60 | 1941 | 2017 | 76 | 40 | 20 | 9 | ea | 20000 | 180000 | 267470.5313
4C | Wooden framed single glazed stained windows - church - 22 smaller windows | 60 | 1941 | 2017 | 76 | 40 | 20 | 22 | ea | 7000 | 154000 | 228835.899
4D | Vinyl framed double glazed windows - daycare, office & fireside room - 24 windows | 35 | 1997 | 2017 | 20 | 20 | 15 | 24 | ea | 2500 | 60000 | 80752.1003
4E | Wooden framed windows - painting frames and trims | 10 | 2014 | 2017 | 3 | 9 | 1 | 101 | ea | 80 | 8080 | 8241.6
5A | Wooden framed & solid wooden swing doors (double and single doors) - 18 lvs | 50 | 1960 | 2017 | 57 | 30 | 20 | 18 | lvs | 4000 | 72000 | 106988.2125
5B | Hollow-core steel door to mechanical room | 50 | 1960 | 2017 | 57 | 35 | 15 | 1 | ea | 2000 | 2000 | 2691.7367
5C | Metal clad swing door with glazed panel to caretakers suite | 35 | 1990 | 2017 | 27 | 34 | 1 | 1 | ea | 1000 | 1000 | 1020
6A | Sloped roofing with asphalt shingles (church and main hall) - old roof | 22 | 1999 | 2017 | 18 | 21 | 1 | 15000 | sf | 5.25 | 78750 | 80325
6B | Sloped roofing with asphalt shingles (offices) - new roof | 22 | 2014 | 2017 | 3 | 3 | 19 | 1900 | sf | 5.25 | 9975 | 14531.6914
6C | Two-ply SBS bitumen membrane roofing (church) - old roof | 22 | 1999 | 2017 | 18 | 17 | 5 | 1800 | sf | 15 | 27000 | 29810.1817
6D | Two-ply SBS bitumen membrane roofing (offices) - new roof | 22 | 2014 | 2017 | 3 | 3 | 19 | 1025 | sf | 15 | 15375 | 22398.4718
7A | Fittings - Kitchen cabinetry fittings main floor - re-faced | 30 | 1980 | 2017 | 37 | 25 | 5 | 1 | item | 7000 | 7000 | 7728.5656
7B | Fittings - Kitchen to offices - replacement | 30 | 1990 | 2017 | 27 | 20 | 10 | 1 | item | 3000 | 3000 | 3656.9833
7C | Fittings - Kitchen and washroom cabinetry fittings in caretakers suite | 25 | 2012 | 2017 | 5 | 5 | 20 | 1 | item | 6000 | 6000 | 8915.6844
7D | Fittings - Kitchen cabinetry fittings to sacristy | 30 | 1980 | 2017 | 37 | 22 | 8 | 1 | item | 6000 | 6000 | 7029.9563
7E | Fittings - Washroom cabinetry fittings | 30 | 2010 | 2017 | 7 | 7 | 23 | 1 | item | 2000 | 2000 | 3153.7985
7F | Fittings - Kitchen, storage and washroom cabinetry fittings - pre-school - Crown | 30 | 2005 | 2017 | 12 | 12 | 18 | 1 | item | 12000 | 12000 | 17138.955
7G | Fittings - Kitchen, storage and washroom cabinetry fittings - pre-school - Tom Thumb | 30 | 2010 | 2017 | 7 | 7 | 23 | 1 | item | 20000 | 20000 | 31537.9853
8A | Interior doors - hardware replacement | 35 | 1960 | 2017 | 57 | 33 | 2 | 40 | ea | 100 | 4000 | 4161.6
8B | Interior doors and trims - painting | 15 | 2000 | 2017 | 17 | 14 | 1 | 60 | ea | 50 | 3000 | 3060
9A | Wall finishes - church, sacristy, chapel etc | 20 | 2000 | 2017 | 17 | 18 | 2 | 10000 | sf | 0.8 | 8000 | 8323.2
9B | Wall and ceiling finishes - gym, stage and washrooms | 20 | 2000 | 2017 | 17 | 17 | 3 | 10000 | sf | 0.8 | 8000 | 8489.664
9C | Wall finishes - upstairs offices | 20 | 2000 | 2017 | 17 | 17 | 3 | 1 | item | 1800 | 1800 | 1910.1744
9D | Wall finishes - fireside room & kitchen | 15 | 2005 | 2017 | 12 | 10 | 5 | 2500 | sf | 0.8 | 2000 | 2208.1616
9E | Wall finishes - pre-schools | 10 | 2010 | 2017 | 7 | 7 | 3 | 3500 | sf | 0.8 | 2800 | 2971.3824
9F | Wall and ceiling finishes - caretaker suite | 12 | 2012 | 2017 | 5 | 5 | 7 | 1 | item | 1600 | 1600 | 1837.8971
9G | Wall finishes - totem room and washrooms | 20 | 2002 | 2017 | 15 | 15 | 5 | 1400 | sf | 0.8 | 1120 | 1236.5705
9H | Wall finishes - lobbies | 15 | 2005 | 2017 | 12 | 12 | 3 | 1 | item | 300 | 300 | 318.3624
10A | Floor finishes - carpet - church, chapel etc. | 20 | 2004 | 2017 | 13 | 13 | 7 | 371.43 | sf | 10 | 3714.3 | 4266.5632
10B | Floor finishes - gym - wooden floor - sand and re-finish | 20 | 1995 | 2017 | 22 | 18 | 2 | 2860 | sf | 3.5 | 10010 | 10414.404
10C | Floor finishes - second floor - carpets to offices | 25 | 1990 | 2017 | 27 | 23 | 2 | 700 | sf | 5 | 3500 | 3641.4
10D | Floor finishes - second floor - carpets to rectors office | 25 | 2013 | 2017 | 4 | 4 | 21 | 200 | sf | 5 | 1000 | 1515.6663
10E | Floor finishes - second floor - laminate flooring to hallways | 25 | 2011 | 2017 | 6 | 17 | 8 | 400 | sf | 7.5 | 3000 | 3514.9781
10F | Floor finishes - fireside room | 15 | 2005 | 2017 | 12 | 10 | 5 | 1700 | sf | 5 | 8500 | 9384.6868
10G | Floor finishes - daycare - vinyl & carpet | 20 | 2003 | 2017 | 14 | 14 | 6 | 2700 | sf | 5 | 13500 | 15203.1927
10H | Floor finishes - caretaker suite | 15 | 2012 | 2017 | 5 | 5 | 10 | 1000 | sf | 5 | 5000 | 6094.9721
10J | Floor finishes - totem room | 20 | 2005 | 2017 | 12 | 12 | 8 | 220 | sf | 5 | 1100 | 1288.8253
10K | Floor finishes - lobbies - wooden floor - sand and stain | 20 | 2000 | 2017 | 17 | 17 | 3 | 100 | sf | 3.5 | 350 | 371.4228
10L | Floor finishes - stairs to office and caretakers suite - carpet | 20 | 1995 | 2017 | 22 | 19 | 1 | 2 | item | 450 | 900 | 918
10M | Floor finishes - kitchen main floor - vinyl flooring | 20 | 2000 | 2017 | 17 | 17 | 3 | 200 | sf | 5 | 1000 | 1061.208
10L | Floor finishes - washrooms and hallway adjacent hall - vinyl | 20 | 2010 | 2017 | 7 | 7 | 13 | 300 | sf | 5 | 1500 | 1940.4099
10N | Floor finishes - sacristy, office, hallway and washroom in church | 20 | 2000 | 2017 | 17 | 15 | 5 | 300 | sf | 5 | 1500 | 1656.1212
11A | Ceiling finishes - offices | 20 | 2003 | 2017 | 14 | 14 | 6 | 1100 | sf | 0.7 | 770 | 867.1451
11B | Ceiling finishes - church - wooden | 40 | 1990 | 2017 | 27 | 27 | 13 | 5500 | sf | 3 | 16500 | 21344.5094
11C | Ceiling finishes - daycare | 20 | 2005 | 2017 | 12 | 12 | 8 | 2700 | sf | 0.7 | 1890 | 2214.4362
11D | Ceiling finishes - fireside room and kitchen | 20 | 2003 | 2017 | 14 | 14 | 6 | 1900 | sf | 0.7 | 1330 | 1497.796
11E | Ceiling finishes - totem room and washrooms | 20 | 2005 | 2017 | 12 | 12 | 8 | 520 | sf | 0.7 | 364 | 426.484
12A | Plumbing fixtures - 5% of fixtures | 30 | 1990 | 2017 | 27 | 27 | 3 | 1 | item | 1030 | 1030 | 1093.0442
12B | Plumbing fixtures - 20% of fixtures | 30 | 1995 | 2017 | 22 | 22 | 8 | 1 | item | 4120 | 4120 | 4827.2366
12C | Plumbing fixtures - 60% of fixtures | 30 | 2000 | 2017 | 17 | 17 | 13 | 1 | item | 12360 | 12360 | 15988.978
12D | Plumbing fixtures - 15% of fixtures | 30 | 2010 | 2017 | 7 | 7 | 23 | 1 | item | 3090 | 3090 | 4872.6187
13 | Domestic copper piping - replace with wirsbo piping (7 washrooms and four kitchens - 21 fixtures) | 50 | 1941 | 2017 | 76 | 40 | 10 | 1 | item | 75000 | 75000 | 91424.5815
14 | Rainwater drainage system - aluminum gutters and downpipes | 25 | 1999 | 2017 | 18 | 15 | 10 | 1 | ea | 10000 | 10000 | 12189.9442
15A | Domestic water heater - Rinnai on demand gas fired domestic hot water heater, model R75 RLSe | 15 | 2013 | 2017 | 4 | 4 | 11 | 1 | ea | 4500 | 4500 | 5595.1844
15B | Domestic water heater - General Electric electrical powered domestic hot water heater - for washrooms and caretakers suite | 12 | 2006 | 2017 | 11 | 11 | 1 | 1 | ea | 900 | 900 | 918
15C | Domestic water heater - space heater in washroom | 10 | 2017 | 2017 | 0 | 0 | 10 | 1 | ea | 600 | 600 | 731.3967
16 | Hot water boiler - Futera gas fired hot water hydronic heating boiler, model HW104437 and Tekmar controls | 22 | 2005 | 2017 | 12 | 12 | 10 | 1 | item | 25000 | 25000 | 30474.8605
17A | Primary HVAC pumps - Bell and Gossett & Taco pumps in boiler room | 10 | 2013 | 2017 | 4 | 4 | 6 | 2 | ea | 400 | 800 | 900.9299
17B | Primary HVAC pumps - Bell and Gossett pump in HVAC room | 7 | 2011 | 2017 | 6 | 5 | 2 | 1 | item | 600 | 600 | 624.24
18 | Make-up air unit/heat Exchanger (Carrier unit) - for church | 30 | 2013 | 2017 | 4 | 4 | 26 | 1 | item | 35000 | 35000 | 58569.634
19 | Unit heaters - Modine ceiling mounted heaters | 30 | 1990 | 2017 | 27 | 20 | 10 | 2 | ea | 5000 | 10000 | 12189.9442
20A | Unit heaters - fan heaters to church | 45 | 1980 | 2017 | 37 | 30 | 15 | 4 | ea | 1500 | 6000 | 8075.21
20B | Unit heater - fan heater in caretakers suite | 25 | 2000 | 2017 | 17 | 24 | 1 | 1 | ea | 300 | 300 | 306
21 | Electrical baseboard heaters & thermostats in offices | 35 | 1990 | 2017 | 27 | 27 | 8 | 3 | ea | 350 | 1050 | 1230.2424
22A | Controls and instrumentation - Neptronic thermostat controls - church | 25 | 2017 | 2017 | 0 | 0 | 25 | 1 | ea | 1000 | 1000 | 1640.606
22B | Controls and instrumentation - Delta control valves for hydronic piping. | 8 | 2013 | 2017 | 4 | 4 | 4 | 3 | ea | 700 | 2100 | 2273.1075
22C | Controls and instrumentation - hall, offices & daycare - Danfoss style valves to regulate temperature on second floor | 25 | 2017 | 2017 | 0 | 24 | 1 | 9 | ea | 700 | 6300 | 6426
22D | Controls and instrumentation - tempering/mixing valve for Crown pre-school | 25 | 2017 | 2017 | 0 | 24 | 1 | 1 | item | 1000 | 1000 | 1020
22E | Controls and instrumentation - Belimo motor diverting valves for make-up air unit | 5 | 2011 | 2017 | 6 | 3 | 2 | 1 | item | 1000 | 1000 | 1040.4
23 | Other HVAC systems and equipment - ASME expansion tank with bladder | 35 | 2013 | 2017 | 4 | 4 | 31 | 1 | item | 3500 | 3500 | 6466.5609
24A | Main electrical service and distribution - old breaker panels | 50 | 1941 | 2017 | 76 | 48 | 2 | 1 | item | 9450 | 9450 | 9831.78
24B | Main electrical service and distribution - old breaker panels | 50 | 1941 | 2017 | 76 | 42 | 8 | 1 | item | 9450 | 9450 | 11072.1812
24C | Main electrical service and distribution - new breaker panels | 50 | 2000 | 2017 | 17 | 17 | 33 | 1 | item | 9000 | 9000 | 17300.0826
25A | Light fixtures - 10% of light fixtures | 35 | 1980 | 2017 | 37 | 32 | 3 | 0.1 | % | 44000 | 4400 | 4669.3152
25B | Light fixtures - 90% of light fixtures | 35 | 1990 | 2017 | 27 | 22 | 13 | 0.9 | % | 44000 | 39600 | 51226.8226
26A | Fire alarm panel - Mircom Series 1000 | 25 | 2001 | 2017 | 16 | 16 | 9 | 1 | item | 5000 | 5000 | 5975.4628
26B | Fire alarm components - heat detectors | 25 | 2000 | 2017 | 17 | 18 | 7 | 1 | item | 500 | 500 | 574.3428
27A | Exit and emergency light fixtures - old | 30 | 1960 | 2017 | 57 | 28 | 2 | 4 | ea | 200 | 800 | 832.32
27B | Exit and emergency light fixtures - new | 30 | 2000 | 2017 | 17 | 17 | 13 | 10 | ea | 200 | 2000 | 2587.2133
28A | Residential appliances - dishwasher in main kitchen | 20 | 1991 | 2017 | 26 | 19 | 1 | 1 | item | 5000 | 5000 | 5100
28B | Residential appliances - two ovens and two fans in main kitchen | 15 | 2005 | 2017 | 12 | 11 | 4 | 1 | item | 2000 | 2000 | 2164.8643
28C | Residential appliances - fridge in main kitchen | 8 | 2010 | 2017 | 7 | 7 | 1 | 1 | item | 700 | 700 | 714
28D | Residential appliances - in caretakers suite - oven, fan, fridge and dishwasher. | 12 | 2012 | 2017 | 5 | 5 | 7 | 1 | item | 2000 | 2000 | 2297.3713
28E | Residential appliances - pre-school - Tom Thumb | 12 | 2012 | 2017 | 5 | 6 | 6 | 1 | item | 1500 | 1500 | 1689.2436
28F | Residential appliances - pre-school - Crown | 12 | 2005 | 2017 | 12 | 8 | 4 | 1 | item | 1200 | 1200 | 1298.9186
28G | Residential appliances - Laundry room - combined washer/dryer | 8 | 2012 | 2017 | 5 | 5 | 3 | 1 | item | 1200 | 1200 | 1273.4496
29 | Ricoh office Copier | 15 | 2012 | 2017 | 5 | 5 | 10 | 1 | item | 23000 | 23000 | 28036.8717
30 | Fixed furnishings - blinds | 20 | 2005 | 2017 | 12 | 12 | 8 | 40 | ea | 100 | 4000 | 4686.6375
31 | Furniture - painting pews | 25 | 1980 | 2017 | 37 | 23 | 2 | 1 | item | 40000 | 40000 | 41616
Siteworks
32 | Concrete stairs - 3 locations - replace | 50 | 1950 | 2017 | 67 | 48 | 2 | 3 | ea | 4265 | 12795 | 13311.918
33 | Pedestrian paving - brick - lift and re-set | 50 | 1950 | 2017 | 67 | 47 | 3 | 1 | item | 8000 | 8000 | 8489.664
34 | Wooden fencing | 25 | 2004 | 2017 | 13 | 13 | 12 | 220 | lf | 30 | 6600 | 8370.3958
35 | Wooden benches | 35 | 1980 | 2017 | 37 | 30 | 5 | 4 | ea | 1000 | 4000 | 4416.3232
36 | Irrigaion sprinkler system | 30 | 1987 | 2017 | 30 | 22 | 8 | 1 | item | 7000 | 7000 | 8201.6157
| TOTAL RESERVES | [9 empty] | 1629340.8 | 2162080.767
| Inflation Rate | 0.02

## Cash Flow
| Cash Flow Analysis | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
|  | Budget Yr | Budget Yr | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year | Year
|  | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | 2031 | 2032 | 2033 | 2034 | 2035 | 2036 | 2037 | 2038 | 2039 | 2040 | 2041 | 2042 | 2043 | 2044 | 2045 | 2046 | 2047
RESERVE FUND EXPENDITURES
ITEM | BUILDING - EXTERIOR
1 | Superstructure - painting to steel fire escape stairs - 2 stairs | 2018: 408; 2025: 468.6638; 2032: 538.3473; 2039: 618.3919; 2046: 710.3379
2A | Superstructure - knock and remove chimney stack to east side of building | 2018: 6158.25
2B | Superstructure - re-point chimney stack for main boiler room in middle of building | 2018: 10281.6
3A | Exterior walls (stucco) at back corner - replacement | 2019: 21848.4
3B | Exterior walls (stucco and cedar siding) - replacement | 2037: 386940.7019
3C | Exterior walls (stucco and cedar siding) - painting | 2024: 19240.4849; 2034: 23454.0438; 2044: 28590.3485
4A | Wooden framed single glazed windows - hall, offices & daycare - 46 ea | 2027: 168221.23
4B | Wooden framed single glazed stained windows - church - 9 large windows | 2037: 267470.5313
4C | Wooden framed single glazed stained windows - church - 22 smaller windows | 2037: 228835.899
4D | Vinyl framed double glazed windows - daycare, office & fireside room - 24 windows | 2032: 80752.1003
4E | Wooden framed windows - painting frames and trims | 2018: 8241.6; 2028: 10046.4644; 2038: 12246.5841
5A | Wooden framed & solid wooden swing doors (double and single doors) - 18 lvs | 2037: 106988.2125
5B | Hollow-core steel door to mechanical room | 2032: 2691.7367
5C | Metal clad swing door with glazed panel to caretakers suite | 2018: 1020
6A | Sloped roofing with asphalt shingles (church and main hall) - old roof | 2018: 80325; 2040: 124180.8171
6B | Sloped roofing with asphalt shingles (offices) - new roof | 2036: 14531.6914
6C | Two-ply SBS bitumen membrane roofing (church) - old roof | 2022: 29810.1817; 2044: 46085.9349
6D | Two-ply SBS bitumen membrane roofing (offices) - new roof | 2036: 22398.4718
7A | Fittings - Kitchen cabinetry fittings main floor - re-faced | 2022: 7728.5656
7B | Fittings - Kitchen to offices - replacement | 2027: 3656.9833
7C | Fittings - Kitchen and washroom cabinetry fittings in caretakers suite | 2037: 8915.6844
7D | Fittings - Kitchen cabinetry fittings to sacristy | 2025: 7029.9563
7E | Fittings - Washroom cabinetry fittings | 2040: 3153.7985
7F | Fittings - Kitchen, storage and washroom cabinetry fittings - pre-school - Crown | 2035: 17138.955
7G | Fittings - Kitchen, storage and washroom cabinetry fittings - pre-school - Tom Thumb | 2040: 31537.9853
8A | Interior doors - hardware replacement | 2019: 4161.6
8B | Interior doors and trims - painting | 2018: 3060; 2033: 4118.3571
9A | Wall finishes - church, sacristy, chapel etc | 2019: 8323.2; 2039: 12367.8374
9B | Wall and ceiling finishes - gym, stage and washrooms | 2020: 8489.664; 2040: 12615.1941
9C | Wall finishes - upstairs offices | 2020: 1910.1744; 2040: 2838.4187
9D | Wall finishes - fireside room & kitchen | 2022: 2208.1616; 2037: 2971.8948
9E | Wall finishes - pre-schools | 2020: 2971.3824; 2030: 3622.0986; 2040: 4415.3179
9F | Wall and ceiling finishes - caretaker suite | 2024: 1837.8971; 2036: 2330.8979
9G | Wall finishes - totem room and washrooms | 2022: 1236.5705; 2042: 1837.4787
9H | Wall finishes - lobbies | 2020: 318.3624; 2035: 428.4739
10A | Floor finishes - carpet - church, chapel etc. | 2024: 4266.5632; 2044: 6339.8884
10B | Floor finishes - gym - wooden floor - sand and re-finish | 2019: 10414.404; 2039: 15475.2565
10C | Floor finishes - second floor - carpets to offices | 2019: 3641.4; 2044: 5974.1027
10D | Floor finishes - second floor - carpets to rectors office | 2038: 1515.6663
10E | Floor finishes - second floor - laminate flooring to hallways | 2025: 3514.9781
10F | Floor finishes - fireside room | 2022: 9384.6868; 2037: 12630.5529
10G | Floor finishes - daycare - vinyl & carpet | 2023: 15203.1927; 2043: 22591.1445
10H | Floor finishes - caretaker suite | 2027: 6094.9721; 2042: 8203.03
10J | Floor finishes - totem room | 2025: 1288.8253; 2045: 1915.1266
10K | Floor finishes - lobbies - wooden floor - sand and stain | 2020: 371.4228; 2040: 551.9147
10L | Floor finishes - stairs to office and caretakers suite - carpet | 2018: 918; 2038: 1364.0997
10M | Floor finishes - kitchen main floor - vinyl flooring | 2020: 1061.208; 2040: 1576.8993
10L | Floor finishes - washrooms and hallway adjacent hall - vinyl | 2030: 1940.4099
10N | Floor finishes - sacristy, office, hallway and washroom in church | 2022: 1656.1212; 2042: 2460.909
11A | Ceiling finishes - offices | 2023: 867.1451; 2043: 1288.5319
11B | Ceiling finishes - church - wooden | 2030: 21344.5094
11C | Ceiling finishes - daycare | 2025: 2214.4362; 2045: 3290.5357
11D | Ceiling finishes - fireside room and kitchen | 2023: 1497.796; 2043: 2225.6461
11E | Ceiling finishes - totem room and washrooms | 2025: 426.484; 2045: 633.7328
12A | Plumbing fixtures - 5% of fixtures | 2020: 1093.0442
12B | Plumbing fixtures - 20% of fixtures | 2025: 4827.2366
12C | Plumbing fixtures - 60% of fixtures | 2030: 15988.978
12D | Plumbing fixtures - 15% of fixtures | 2040: 4872.6187
13 | Domestic copper piping - replace with wirsbo piping (7 washrooms and four kitchens - 21 fixtures) | 2027: 91424.5815
14 | Rainwater drainage system - aluminum gutters and downpipes | 2027: 12189.9442
15A | Domestic water heater - Rinnai on demand gas fired domestic hot water heater, model R75 RLSe | 2028: 5595.1844; 2043: 7530.3815
15B | Domestic water heater - General Electric electrical powered domestic hot water heater - for washrooms and caretakers suite | 2018: 918; 2030: 1164.246; 2042: 1476.5454
15C | Domestic water heater - space heater in washroom | 2027: 731.3967; 2037: 891.5684; 2047: 1086.817
16 | Hot water boiler - Futera gas fired hot water hydronic heating boiler, model HW104437 and Tekmar controls | 2027: 30474.8605
17A | Primary HVAC pumps - Bell and Gossett & Taco pumps in boiler room | 2023: 900.9299; 2033: 1098.2286; 2043: 1338.7345
17B | Primary HVAC pumps - Bell and Gossett pump in HVAC room | 2019: 624.24; 2026: 717.0555; 2033: 823.6714; 2040: 946.1396; 2047: 1086.817
18 | Make-up air unit/heat Exchanger (Carrier unit) - for church | 2043: 58569.634
19 | Unit heaters - Modine ceiling mounted heaters | 2027: 12189.9442
20A | Unit heaters - fan heaters to church | 2032: 8075.21
20B | Unit heater - fan heater in caretakers suite | 2018: 306; 2043: 502.0254
21 | Electrical baseboard heaters & thermostats in offices | 2025: 1230.2424
22A | Controls and instrumentation - Neptronic thermostat controls - church | 2042: 1640.606
22B | Controls and instrumentation - Delta control valves for hydronic piping. | 2021: 2273.1075; 2029: 2663.3078; 2037: 3120.4895; 2045: 3656.1508
22C | Controls and instrumentation - hall, offices & daycare - Danfoss style valves to regulate temperature on second floor | 2018: 6426; 2043: 10542.5341
22D | Controls and instrumentation - tempering/mixing valve for Crown pre-school | 2018: 1020; 2043: 1673.4181
22E | Controls and instrumentation - Belimo motor diverting valves for make-up air unit | 2019: 1040.4; 2024: 1148.6857; 2029: 1268.2418; 2034: 1400.2414; 2039: 1545.9797; 2044: 1706.8865
23 | Other HVAC systems and equipment - ASME expansion tank with bladder
24A | Main electrical service and distribution - old breaker panels | 2019: 9831.78
24B | Main electrical service and distribution - old breaker panels | 2025: 11072.1812
24C | Main electrical service and distribution - new breaker panels
25A | Light fixtures - 10% of light fixtures | 2020: 4669.3152
25B | Light fixtures - 90% of light fixtures | 2030: 51226.8226
26A | Fire alarm panel - Mircom Series 1000 | 2026: 5975.4628
26B | Fire alarm components - heat detectors | 2024: 574.3428
27A | Exit and emergency light fixtures - old | 2019: 832.32
27B | Exit and emergency light fixtures - new | 2030: 2587.2133
28A | Residential appliances - dishwasher in main kitchen | 2018: 5100; 2038: 7578.3317
28B | Residential appliances - two ovens and two fans in main kitchen | 2021: 2164.8643; 2036: 2913.6223
28C | Residential appliances - fridge in main kitchen | 2018: 714; 2026: 836.5648; 2034: 980.169; 2042: 1148.4242
28D | Residential appliances - in caretakers suite - oven, fan, fridge and dishwasher. | 2024: 2297.3713; 2036: 2913.6223
28E | Residential appliances - pre-school - Tom Thumb | 2023: 1689.2436; 2035: 2142.3694; 2047: 2717.0424
28F | Residential appliances - pre-school - Crown | 2021: 1298.9186; 2033: 1647.3428; 2045: 2089.229
28G | Residential appliances - Laundry room - combined washer/dryer | 2020: 1273.4496; 2028: 1492.0492; 2036: 1748.1734; 2044: 2048.2638
29 | Ricoh office Copier | 2027: 28036.8717; 2042: 37733.9379
30 | Fixed furnishings - blinds | 2025: 4686.6375; 2045: 6964.0968
31 | Furniture - painting pews | 2019: 41616; 2044: 68275.4591
Siteworks
32 | Concrete stairs - 3 locations - replace | 2019: 13311.918
33 | Pedestrian paving - brick - lift and re-set | 2020: 8489.664
34 | Wooden fencing | 2029: 8370.3958
35 | Wooden benches | 2022: 4416.3232
36 | Irrigaion sprinkler system | 2025: 8201.6157
| TOTAL EXPENDITURES | 0 | 124896.45 | 115645.662 | 30647.687 | 5736.8904 | 56440.6107 | 20158.3073 | 29365.345 | 44961.2571 | 7529.0832 | 353020.784 | 17133.698 | 12301.9454 | 97874.2777 | 0 | 92057.3943 | 7687.5999 | 25834.4542 | 19709.7982 | 46836.4792 | 1018765.5347 | 22704.6818 | 30007.4654 | 186689.1039 | 0 | 54500.9311 | 106262.0503 | 159020.8838 | 18548.8719 | 710.3379 | 4890.6763

## Plumbing fixtures
| Toilets | Washroom sinks | Urinals | Kitchen sinks | Bathtub
Adjacent fireside room
Mens | 1 | 1 | 1 | 0
Womens | 1 | 1 | 0 | 0
Unisex | 1 | 1 | 0 | 0
Kitchen | 0 | 0 | 0 | 2
Adjacent Stage
Mens | 1 | 1 | 1 | 0
Womens | 1 | 1 | 0 | 0
Church
Mens | 1 | 1 | 0 | 0
Womens | 1 | 1 | 0 | 0
Kitchen | 0 | 0 | 0 | 1
Daycare 1 | 1 | 1 | 0 | 3
Daycare 2 | 1 | 1 | 0 | 1
Caretakers
Washroom and sink | 1 | 1 |  | 1 | 1
Total | 10 | 10 | 2 | 8 | 1
| 5500 | 5500 | 2000 | 5600 | 2000
|  |  | Total | 20600

## Light fixtures
Location | Type | Count | Unit | Rate | Total
Upstairs
Dining area | Fluorescent tube lighting fixtures | 4 | ea | 250 | 1000
Hallway | Fluorescent tube lighting fixtures | 2 | ea | 250 | 500
Hallway | Incandescent fixture | 1 | ea | 75 | 75
Rector office | Incandescent fixture | 2 | ea | 75 | 150
Copy office | Fluorescent tube lighting fixtures | 1 | ea | 250 | 250
Organist | Incandescent fixture | 1 | ea | 75 | 75
Clare Morgan | Fluorescent tube lighting fixtures | 1 | ea | 250 | 250
Waiting Area | Fluorescent tube lighting fixtures | 1 | ea | 250 | 250
Office | Fluorescent tube lighting fixtures | 1 | ea | 250 | 250
Fireside room | Incandescent fixture | 12 | ea | 175 | 2100
Main klitchen | Fluorescent tube lighting fixtures | 7 | ea | 250 | 1750
Main hall | Fluorescent tube lighting fixtures | 6 | ea | 500 | 3000
Main hall | Incandescent fixture | 8 | ea | 200 | 1600
Washrooms | Incandescent fixture | 6 | ea | 75 | 450
Library | Fluorescent tube lighting fixtures | 1 | ea | 250 | 250
Youth room | Incandescent fixture | 4 | ea | 75 | 300
Washrooms and hallway | Incandescent fixture | 6 | ea | 75 | 450
Stage | Incandescent fixture | 3 | ea | 75 | 225
Lobbies | Incandescent fixture | 5 | ea | 75 | 375
Church lobby | Incandescent fixture | 4 | ea | 100 | 400
Church | Hanging incandescent | 17 | ea | 1000 | 17000
Church lobby | Incandescent fixture | 7 | ea | 75 | 525
Church lobby | Hanging incandescent | 1 | ea | 500 | 500
Chaple | Incandescent fixture | 11 | ea | 75 | 825
Chaple | Fluorescent tube lighting fixtures | 4 | ea | 250 | 1000
Gerrys Suite | Incandescent fixture | 8 | ea | 75 | 600
Choir Room | Fluorescent tube lighting fixtures | 3 | ea | 250 | 750
Choir Room | Incandescent fixture | 1 | ea | 75 | 75
Totem | Incandescent fixture | 7 | ea | 75 | 525
Totem | Fluorescent tube lighting fixtures | 10 | ea | 200 | 2000
Storage | Incandescent fixture | 5 | ea | 75 | 375
Storage | Fluorescent tube lighting fixtures | 1 | ea | 200 | 200
Pre-school 1 - Tom Thumb | Fluorescent tube lighting fixtures | 11 | ea | 250 | 2750
Pre-school 1 - Tom Thumb | Incandescent fixture | 6 | ea | 75 | 450
Pre-school 2 - Crown | Fluorescent tube lighting fixtures | 10 | ea | 250 | 2500
Pre-school 2 - Crown | Incandescent fixture | 3 | ea | 75 | 225
| Total | 181 |  |  | 44000

## Electrical
|  | Old | New
Square D 100 amp breaker | Offices - upstair | 1500
Federal Pioneer 125 amp breaker | Mechanical room |  | 2000
Square D 60 amp breaker | Mechanical room | 500
Square D 60 amp breaker | Mechanical room | 500
Electrical MFG panel 100 amp | Mechanical room | 1500
Electrical MFG panel 100 amp | Mechanical room | 1500
Square D 100 amp breaker | Gym | 1500
Square D 125 amp breaker | Lobby | 2000
Cutler Hammer 125 amp breaker | Downstairs |  | 2000
Cutler Hammer 125 amp breaker | Tom Thumb |  | 2000
Federal Electric panel 100 amp | Tom Thumb | 1500
Federal Pioneer 125 amp breaker | In hallway beside totem | 2000
Main breaker - motor circuit switch 400 amp | In hallway beside totem | 6000
Westinghouse 50 amp breaker | Stage | 400
Westinghouse 225 amp breaker | In HVAC room |  | 3000
| Total | 18900 | 9000

## Roofing
Location | Qty | Unit | Rate | Total | GST | Total sloped Old | Total sloped New | Total flat old | Total - flat new
Sloped roofing - old | 9100 | sf | 4.9451 | 45000 | 2250 | 47250
Flat roofing old | 150 | sf | 16.6667 | 2500 | 125 |  |  | 2625
Sloped roofing - old | 5600 | sf | 5.3571 | 30000 | 1500 | 31500
0
Sloped roofing - new | 1500 | sf | 5 | 7500 | 375 |  | 7875
Flat rooing - old | 1600 | sf | 25 | 40000 | 2000 |  |  | 42000
Flat rooing - new | 1025 | sf | 25 | 25625 | 1281.25 |  |  |  | 26906.25
[5 empty] | Total | 78750 | 7875 | 44625 | 26906.25